## Slide 1: RISK Management: Matrix & Activity
GEO
National Conf.
May 2016

## Slide 2: Risk Assessment cycle

## Slide 3: Evaluate RISK
 |  | Probability of Occurrence |  | 
 |  | High | Moderate | Low
Severity of Harm | Severe |  |  | 
 | Moderate |  |  | 
 | Low |  |  | 
Third Axis: Control

## Slide 4: Risk Mitigation
Try to mitigate when:
Severity of Harm | Probability of Occurrence |  | 
 | High | Moderate | Low
Severe |  |  | 
Moderate |  |  | 
Low |  |  | 
Mitigation techniques:
  Identify potential risks
  Adjust project plans, timelines, and/or budgets
  Consider additional training, partners, or resources
  Adjust expectations
  + Moderate to High degree of control over inputs

## Slide 5: Risk Contingency Planning
Try to create contingency plans when:
Severity of Harm | Probability of Occurrence |  | 
 | High | Moderate | Low
Severe |  |  | 
Moderate |  |  | 
Low |  |  | 
Examples of contingency plans:
  Funder sets aside $X for contingencies
  NGO budgets $X for contingencies in original project budget
  Pre-identify areas of flexibility within existing timelines
  Pre-identify additional resources (financial, personnel, partners, training)
  Adjust expectations
  + Low to Moderate degree of control over inputs

## Slide 6: Case Study scenario
Spark! MicroGrants
Spark is an NGO working with local communities to build civil society and implement small-scale development projects. Spark runs a 16-week intensive training for community members to build collective action decision-making skills. The training leads communities through the process of identifying community needs, selecting and planning a community-based project (such as building a school building or purchasing goats to begin a dairy market). Finally, Spark provides a ‘micro-grant’ to fund implementation of that project. They have a proven track record, and solid M&E data to back up their model.
A coffee company approach Spark to expand its work into 14 communities in Uganda, where the company sourced its coffee. The expansion is fully covered by a multi-year grant from the coffee company’s CSR department.

## Slide 7: Actionable Steps
ASK about the potential risks that your grantees do or could face.
TALK with your board, staff, and grantees about your risk profile.
PLAN for risk through mitigation and contingency planning: What happens if…? Create a process for:
    Communication
    Decision-making
    Action

## Slide 8: Additional Resources
SWOT Analysis Templates/Examples
  Charity Commission SWOT Analysis
  New Philanthropy Capital SWOT Analysis
  American Red Cross SWOT Analysis
PESTLE Templates/Examples
  Charity Commission PESTLE Analysis
  Development Training for Girls PEST Analysis
Risk Matrices Templates/Examples
  Open Road Alliance Risk Severity Matrix
  KnowHow Nonprofit Risk Classification Matrix
  Blandin Foundation Risk/Reward Assessment (GEO list-serve)
  Charity Commission Risk Matrix
  PESTLE
  Political
  Economic
  Social
  Transportation
  Logistical
  Environment

## Slide 9
END

## Slide 10: Act: Mitigation v. contingency
Mitigation: when risks can be managed through effective planning.
Contingency: when risks are not predictable or cannot be managed through effective planning.
  Moderate to High Severity
  Moderate to High Likelihood and
  Moderate to High degree of influence over context
  Moderate to High Severity
  Low Likelihood and/or
  Low degree of control over context

## Slide 11: Nitty Gritty
Mitigation techniques:
  Identify potential risks
  Adjust project plans, timelines, and/or budgets
  Consider additional training, partners, or resources
  Adjust expectations
Examples of contingency plans:
  Funder sets aside $X for contingencies
  NGO budgets $X for contingencies in original project budget
  Pre-identify areas of flexibility within existing timelines
  Pre-identify additional resources (financial, personnel, partners, training)
  Adjust expectations

## Slide 12: Managing Risk: Control
X = Probability Y = Severity Z = Control

## Slide 13: THIS IS NOT A MATH TEST
Determining what is or isn’t in our control, and what is of high or low probability and severity is art (or experience), not science.